## Slide 1: Greening Relevance in Operations in Western-Balkans Tertiary-Education Habitats
ERASMUS-EDU-2022-CBHE-STRAND-1
ERASMUS-EDU-2022-CBHE
101083212
ERASMUS-AG-LS

## Slide 2: GROWTH 101083212 Basic information
Consortium
8 partners from 5 countries (Bosnia and Herzegovina, Montenegro, Serbia, Germany, Slovakia)
7 higher education institutions
1 non-academic partner
Duration
01.03.2023. – 01.03.2026.
Budget
EU requested amount (90%): 400.000 EUR

## Slide 3: GROWTH 101083212 Partners
Bosnia and Herzegovina | BE 001 | University of Bijeljina - COORDINATOR
 | BE 002 | University Herzegovina
 | BE 003 | University College CEPS Kiseljak
Montenegro | BE 004 | Adriatic University Bar
 | BE 008 | Socioekonomski centar Crne Gore
Serbia | BE 005 | Academy of applied preschool teaching and health studies
Germany | BE 006 | Hochschule Weihenstephan-Triesdorf
Slovakia | BE 007 | Slovak University of Agriculture in Nitra

## Slide 4: GROWTH 101083212 General objective
NARRATIVE SUMMARY OF THE INTERVENTION LOGIC | OBJECTIVELY VERIFIABLE INDICATORS | MEANS OF VERIFICATION | IMPORTANT ASSUMPTIONS AND PREREQUISITES
Goal (general objective) To assist Western Balkans green transition efforts | 1) Evidence of green transition mechanisms in place at Uni campuses until 2025 2) Evidence of green learning culture and support provision at HEIs 3) Students and staff indicate overall satisfaction with introduced transformation measures | 1) Partner HEIs annual reports, external evaluation report 2) Optimized Partner Green services and mechanism on Campus progress evaluations, external evaluation, partner HEIs self-evaluation reports | Green Agenda and EU Green Deal remain highly in political agendas of Western Balkans potential candidate and candidate states

## Slide 5: GROWTH 101083212 Specific objectives
NARRATIVE SUMMARY OF THE INTERVENTION LOGIC | OBJECTIVELY VERIFIABLE INDICATORS | MEANS OF VERIFICATION | IMPORTANT ASSUMPTIONS AND PREREQUISITES
Purpose (specific Objectives) SO1) To make higher education and research in the Western Balkans more environmentally conscious SO2) To introduce green education methodologies and practices in 4 partner higher education institutions | SOin1.1) Number of measures introduced at HEIs to support green transition in 2 partner countries (20) SOin1.2) Number of managements, teaching and non-teaching staff (120-150) improved competences on green transition and HEIs role in the process SOin1.3) Number of partners HEIs implemented the principles of green transition (4) SOin2.1) Number of partners HEIs optimized their working environment and learning tools and equipment (4) SOin2.2) Number of partners HEIs adopted institutional policies ensuring green transition (4) SOin2.3) Number of ToT teams created at partner HEIs (4) and number of trained teaching staff (48) | SOin1.1) external evaluation report SOin1.2) External evaluation report SOin1.3) Partner HEIs annual reports SOin2.1) Partner HEIs websites, external evaluation report SOin2.2) Partner HEIs annual reports SOin2.3) Partner HEIs annual reports | Assumption: All HEIs leaders in the Western Balkans understand the needs for greening their campuses and buildings Assumption: All HEIs are ready to promote their success stories with local, national and transnational stakeholders and counterparts

## Slide 6: GROWTH 101083212 Governance Structure
Project Consortium Board (PCB)
8 partners
Project coordinator
(chair of PCB)
UBN
WP3
AVMSS
WP2
HSWT
WP1
UBN
National coordinator
Bosnia and Herzegovina
UBN
National coordinator
Montenegro
AUB
Quality Assurance
Committee/ M&E team
8 partners
WP6
UBN
WP5
CEPS
WP4
SUA

## Slide 7: GROWTH 101083212 Workpackages Overview and Deliverables
GROWTH
WP1 Project preparation
WP2 Optimization of HEIs environment
WP3 Green transition in teaching, learning and research
WP5 Communication & exploitation
WP4 Introduction of digital & sustainable academic mobility
WP6 Project management and quality control
D1.1.1 | Project teams created
D1.1.2 | Implementation tools adopted
D1.2 | Teaching and administrative/technical staff improved project implementation, financial management and quality control skills
D1.3 | Website ’Towards green university’’ created for public use
D1.4. | Needs analysis update report
D1.5 | 2 national conferences
D2.1 | Management, teaching, admin. & technical staff improved knowledge on climate-neutral universities
D2.2 | Equipment purchased and installed
D2.3 | Towards green university strategy prepared for adoption at 4 WB partner HEIs
D2.4 | E-manual
D2.5 | Teacher staff trained on ToT skills in 3 fields
D2.6 | Study visit and learning about recycling practices and renewable energy efforts carried out
D2.7 | 4 WB partner HEI buildings equipped with recycling points with instructions
D2.8 | Open air classrooms created
D2.9 | 4 WB partner HEIs improved energy use systems on the campuses
D3.1 | 2.1) Management, teaching, adm2.8) in. & technical staff improved knowledge on climate-neutral universities.
D3.2 | Video tutorial
D3.3 | Study visit and learning about student hackathons carried out
D3.4 | Green university innovation hackathons prepared for implementation
D4.1 | Administrative and teaching staff trained on student and staff mobility
D4.2 | Student parliaments and organizations trained on student mobility
D4.3 | E-guidelines
D4.4 | Administrative and management staff learned about mobility practices
D4.5 | 3 EU partner HEIs provided 6 months e-mentoring support to administrative staff at 4 WB partner HEIs
D5.1 | Website recognized by the specific and general communities
D5.2 | Stakeholders made aware of green university policyTowards green university
D5.3 | E-newsletter Towards green university
D5.4 | WB Partner institution teaching and administrative & technical staff trained on recycling culture, green energy sources, infrastructure
D5.5 | 4 institutional hackathon reports
D5.6 | 2 national conference reports
D6.1 | Ensured regular project coordination
D6.2 | Ensured regular project quality control
D6.3 | Results and costs internally verified
D6.4 | Independent evaluation report

## Slide 8: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
T1.1 | Kick off meeting, creation of project teams and adoption of implementation documents
T1.2 | Initial staff training sessions on project implementation, financial management and quality
T1.3 | Signing of partnership agreements
T1.4 | Creation of ‘’Towards green university’’ website
T1.5 | Update needs analysis of partner WB HEIs to strengthen university green agenda
T1.6 | Introduction conferences in BA and ME
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS1 | Partnership agreements concluded between the coordinator and partner institutions | WP1 | UBN | Partnership agreements signed between the project coordinator and each partner. They will regulate the rights and obligations within the partnership, and distribution of tasks and responsibilities relating to project implementation and achievement of project results. | M1 | Signed partnership agreements
D1.1.1 | Project teams created
D1.1.2 | Implementation tools adopted
D1.1.3 | Partnership agreement – model as for 2020
D1.2 | Teaching and administrative/technical staff improved project implementation, financial management and quality control skills
D1.3 | Website ’Towards green university’’ created for public use
D1.4. | Needs analysis update report
D1.5 | 2 national conferences
Activities
Deliverables

## Slide 9: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.1 | Kick off meeting, creation of project teams and adoption of implementation documents | The kick-off meeting will be organized in a virtual environment and it will host representatives of all partner institutions. It will be organised by the leading partner UBN in the course of the first month of the project (M1). Activities are planned to last for 2 working days and they will be realised in the following manner: 1) the partnership will be acquainted with their respective contractual obligations, the rules of the Action (Erasmus + CBHE), and key aspects of the financial management and administration procedures; 2) the partnership will be introduced in detail to the project structure, devised activities and interventions, results to be achieved; partnership agreement and project implementation tools will be discussed and agreed upon; 3) planned project teams will be established and the partnership will agree on pace, type and frequency of communication. The meeting outcomes will be as follows: agreement on further steps and each partner´s tasks and obligations; structuring project teams (Steering Committee, Quality team, Communication team, + lead/co-lead WP teams); approved set of project implementation documents (Communication, Dissemination and Exploitation Plan, Gantt chart, and Rules of Procedure).
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E1.1 | Participants: UBN, SVEHERC, CEPS, AUB, AVMSS, HSWT, SUA, SECCG | Kick-off meeting (Activity T.1.1) | Meeting] | Areas: Project description, results, activities, indicators, task division, budget, timeline, grant agreement, partnership agreement, project teams, implementation tools, ] | Virtual platform | 2 | 24 (3 UBN, 3 SVEHERC, 3 CEPS, 3 AUB, 3 AVMSS, 3 HSWT, 3 SUA, 3 SECCG)

## Slide 10: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.2 | Initial staff training sessions on project implementation, financial management and quality | The second virtual meeting will be held in the course of the second month (M2) and it will be hosted by P6 (HSWT). The meeting is planned to last for 2 working days and it is intended for project coordinators, members of each project team previously defined during the kick-off meeting, and administrative and financial team members. In the course of this meeting the participants will be trained on project implementation activities: work package coordination, task implementation, monitoring and evaluation of project activities, manners in which project materials and document will be kept and stored and how partners will have access to them, and about the form and frequency of reporting. As to financial management, participants will be trained on how to run financial documentation and keep the financial records: the programme rules regarding different categories of costs (staff costs, travel and subsistence costs, equipment and subcontracting costs, indirect costs, co-financing requirements), time sheets, internal verification procedures, etc. The third segment of these virtual meetings is dedicated to quality assurance and control. Through this training, the relevant staff will be introduced to QA approach and QA plans and instruments previously drafted by the QA team and finalized by participants during the training session. Minimum 48 staff members will be trained in the course of three planned training sessions (16 per session, whereby 30% are expected to be female participants)
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E1.2 | Training delivered by HSWT Participants: UBN, SVEHERC, CEPS, AUB, AVMSS, HSWT, SUA, SECCG, | Staff training on project implementation, financial management and quality control (Activity T1.2) | Training | Topics: project implementation, financial management and quality control | Virtual platform | 3 | 48 (12 UBN, 12 SVEHERC, 12 CEPS, 12 AUB)

## Slide 11: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.3 | Signing of partnership agreements | Once all partners have agreed on the mutual form of the partner agreement, on individual tasks, roles and obligations, as well as on consequences in case of violation of rights and obligations, partnership agreements will be signed and stored according to partners´ initial agreement.
Task No | Task Name | Description
T1.4 | Creation of ‘’Towards green university’’ website | This activity will be initiated in the third month (M3) of the project and it will be a joint activity of all project partners, led by P3 and P5. All participants will be engaged in providing ideas and solution regarding the website visual and structural design, while partners P3 and P5 will take care of the actual creation process.

## Slide 12: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.5 | Update needs analysis of partner WB HEIs to strengthen university green agenda | Upon concluding initial preparatory activities, the project team led by UBN will prepare and conduct an updated needs analysis with the aim of strengthening university green agenda. The updated needs analysis will serve to build up and amend the existing notions of current needs and confirm the strong base for project interventions. It will clearly indicate and/or reconfirm the most acute points requiring urgent intervention and pinpoint suitable paths for enhancing the four HEIs green transition. The activity will be led by the UBN, but it will be a result of a joint effort of all four partner HEIs from Western Balkans (B&H and Montenegro). As to methodology, the needs analysis will be informed by the most recent developments at partner HEIs reflected in the latest activities, evaluation reports and strategies adopted in partner´s institutions. The report on updated needs analysis will be the result of joint effort, but it will be developed and written in English by the UBN. This is the key activity which will enable the project´s transition to WP2.

## Slide 13: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.6 | Introduction conferences in BA and ME | Two conferences are planned within this work package and they will be held in the hybrid environment. Purpose of these conferences will be to present the main findings of the updated needs analysis from four HEIs as well as to present the participants and wider audience with the main project topic (green transition through green practices and environmental awareness resulting in environmentally friendly behaviours and actions) and possible interventions.
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E1.3 | Conference hosted by: UBN, SVEHERC, CEPS, AUB Participants: students, teaching staff, non-teaching staff, management, researchers, local community | Introduction conferences in BA and ME (Activity T1.6) | Conference | Four HEIs from B&H and Montenegro will host two introductory conferences to introduce target groups and all potential stakeholders to projects ambitions and aspirations with regards to the topic of environmental awareness climate neutrality and green transition. | UBN, SVEHERC, CEPS, AUB | 1 | Total: 150

## Slide 14: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
D1.1.1 | Project teams created
D1.1.2 | Implementation tools adopted
D1.1.3 | Partnership agreement – model as for 2020
D1.2 | Teaching and administrative/technical staff improved project implementation, financial management and quality control skills
D1.3 | Website ’Towards green university’’ created for public use
D1.4. | Needs analysis update report
D1.5 | 2 national conferences
Deliverables
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS1 | Partnership agreements concluded between the coordinator and partner institutions | WP1 | UBN | Partnership agreements signed between the project coordinator and each partner. They will regulate the rights and obligations within the partnership, and distribution of tasks and responsibilities relating to project implementation and achievement of project results. | M1 | Signed partnership agreements
WPs/ t | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
WP1 | X | X | X | X | X | X | X | X | X | X | X | X

## Slide 15: Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB
Activities
Deliverables
T2.1 | Introduction seminar for management, administrative & technical staff on climate-neutral universities (management, campuses, transportation, heating, research)
T2.2 | Procurement of equipment
T2.3 | Workshops on the creation of Towards green university strategy’’
T2.4 | Creation of e-manual on climate neutral universities in Western Balkans
T2.5 | ToT program on green universities for teaching staff
T2.6 | Study visit to HSWT, Germany, to learn about recycling practices and renewable energy efforts
T2.7 | Provision of recycling points with instructions around buildings and campuses and training of technical staff on recycling points management
T2.8 | Creation and equipping of campus gardens - open air classrooms
T2.9 | Introduction of renewable energy efforts at campuses and LED lights use
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS2 | Competent bodies at 4 HEIs adopted ’Towards green university strategies’’ | WP2 | HSWT | Towards green university strategy will be adopted by University Senates of four target Western Balkans universities. The strategy comprises the plan of action of creating, nurturing and maintaining green universities. | M27 | Official decision of 4 University Senates.
D2.1 | Management, teaching, admin. & technical staff improved knowledge on climate-neutral universities
D2.2 | Equipment purchased and installed
D2.3 | Towards green university strategy prepared for adoption at 4 WB partner HEIs
D2.4 | E-manual
D2.5 | Teacher staff trained on ToT skills in 3 fields
D2.6 | Study visit and learning about recycling practices and renewable energy efforts carried out
D2.7 | 4 WB partner HEI buildings equipped with recycling points with instructions
D2.8 | Open air classrooms created
D2.9 | 4 WB partner HEIs improved energy use systems on the campuses

## Slide 16
Task No | Task Name | Description
T2.1 | Introduction seminar for management, administrative & technical staff on climate-neutral universities (management, campuses, transportation, heating, research) | In the course of M8, a two-day virtual seminar will be organised for technical and administrative staff, as well as for the management on the topic of climate neutral universities. The staff will be introduced to the concept of green, i.e. climate neutral universities: how are those universities different, how do energy efficiency, renewable sources and reduced consumption lead to the creation of green universities, what individual and institutional habits need to be changed and to what purpose, how different institutional services can address the issue of environmental sustainability, what legal and technical mechanisms needs to be put in place to create a green university, etc. The seminar is planned to last for 2 days (5 hours per day). It is intended for 36 participants in total, and it is expected that at least 30% will be women.
Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E2.1 | Seminar delivered by HSWT Participants: management, administrative & technical staff from: UBN, SVEHERC, CEPS, AUB | Seminar for management, admin. & technical staff on climate-neutral universities (management, campuses, transportation, heating, research) (Activity T2.1) | Seminar (training) | The staff will be introduced to the concept of green, i.e. climate neutral universities: how are those universities different, how do energy efficiency, renewable sources and reduced consumption lead to the creation of green universities, what individual and institutional habits need to be changed and to what purpose, how different institutional services can address the issue of environmental sustainability, what legal and technical mechanisms needs to be put in place to create a green university, etc | Virtual platform | 2 | 36 (9 UBN, 9 SVEHERC, 9 CEPS, 9 AUB)

## Slide 17
Task No | Task Name | Description
T2.2 | Procurement of equipment | The procurement procedure for the equipment will start in the 4th month of the project, after the financial management training and the necessary market analysis of suppliers of specified equipment. The team of financial officers will prepare the tendering procedure and conduct the procurement procedure in accordance with the provisions of the Grant agreement, partnership agreements and national legislations. The equipment will be installed at 4 partner HEIs and will be used by staff and students during project implementation and after the project lifetime.
Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB
3 recycling containers for separation of paper, glass and metal garbage to be placed at university campus
4 Laptops
Set of benches for open air classrooms
Water-to-water heat pumps (geothermal heatpumps)
UBN
3 recycling containers for separation of paper, glass and metal garbage to be placed at university campus
Set of benches for open air classrooms
5 Laptops
3 sets of HD video cameras, web video cameras, wireless microphone
SVEHERC
3 recycling containers for separation of paper, glass and metal garbage to be placed at university campus
Air Quality Test Kit (Pro)
SoundPLAN (Software/2 yrs licence)
Set of benches for open air classrooms
CEPS
3 recycling containers for separation of paper, glass and metal garbage to be placed at university campus
Set of benches for open air classrooms
3D printer
3D digital scanner
3x LAPTOP 17-CH1035NR
3x LAPTOP 17-CH1035NR
AUB

## Slide 18
Task No | Task Name | Description
T2.3 | Workshops on the creation of Towards green university strategy’’ | In order to initiate the process of creating the so-called green universities it is necessary to draft the necessary plan of action to achieve this long-term goal. This plan of action, i.e. the strategy should comprise the necessary analysis of the current state of affairs, steps and guidelines towards the set objectives and milestones, mandatory actions and procedures, defined actors and factors of planned actions. The strategy is to be devised by four target HEIs in collaboration with the partnership. There will be 4 strategies drafted as a result of workshops, which will be held in the virtual environment. Workshops will be held in M18. Three workshops are planned to take place. During the first workshop the participants (4 per institution) will analyse the current state of affairs in target HEIs in the Western Balkans and define acute points and needs. During the second workshop participants will define the main objectives and milestones, identify the necessary steps and procedures and define the manner of attaining the objectives. During the third workshop participants will peer-review their draft strategies and prepare them for finalization which will be done after the third workshop. All three workshops will last for 2 days each, 5 hours per day. There will be 4 participants per institution and it is expected that 30% will be female participants.
Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E2.2 | Workshop facilitated by: HSWT Participants: UBN, SVEHERC, CEPS, AUB | Workshop on the creation of Towards green university strategy (Activity T2.3) | Workshop | The strategy should comprise the necessary analysis of the current state of affairs, steps and guidelines towards the set objectives and milestones, mandatory actions and procedures, defined actors and factors of planned actions. | Virtual platform | 3 | 48 (12 UBN, 12 SVEHERC, 12 CEPS, 12 AUB)

## Slide 19
Task No | Task Name | Description
T2.4 | Creation of e-manual on climate neutral universities in Western Balkans | Upon finishing the first workshop, the WP2 team led by HSWT will embark on devising a toolkit on climate neutral universities. This toolkit will have the form of an e-manual comprising the necessary information and recommendation relevant for understanding, creating and maintaining climate neutral universities. The e-manual will contain written instructions and recommendations for the four HEIs staff to follow in order to deliver further training in climate neutral universities to staff, students and all other interested stakeholders. The e-manual will be available in English, and it will be uploaded to the project website, as well as to individual partners´ websites.
Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB

## Slide 20
Task No | Task Name | Description
T2.5 | ToT program on green universities for teaching staff | Training of trainers or ToT programmes will encompass five training sessions which will serve to capacitate the staff of four target universities to further educate their colleagues on the concept of green university: how to educate further on green universities, how to build, embrace and nurture recycling culture, green energy sources and infrastructure, etc. Sixteen staff members in total will be trained through the afore-mentioned ToT programmes and it is expected that 30% will be female staff. The programme will be conducted in M18 and it will be led by P7 partner.
Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E2.3 | Training facilitated by: SUA Participants: UBN, SVEHERC, CEPS, AUB | Training of trainers -programme on green universities for teaching staff (Activity T2.5) | Training | The training will serve to capacitate the staff of four target universities to further educate their colleagues on the concept of green university: how to educate further on green universities, how to build, embrace and nurture recycling culture, green energy sources and infrastructure | Virtual platform | 2 | 16 (4 UBN, 4 SVEHERC, 4 CEPS, 4 AUB)

## Slide 21
Task No | Task Name | Description
T2.6 | Study visit to HSWT, Germany, to learn about recycling practices and renewable energy efforts | This study visit will be organized and hosted by HSWT. Sixteen staff members will be in the situation to see on-site green practices at the university which has already obtained a green card, i.e. has embraced green practices. Study visit will take place in M12 and it will gather 16 participants (4 per target partner university). It is expected that 30% of participants will be women.
Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E2.4 | Workshop facilitated by HSWT Participants: UBN, SVEHERC, CEPS, AUB | Workshop dedicated to learning about recycling practices and renewable energy efforts (Activity T2.6) | Study visit and Workshop | Workshop will be organised to enable staff members to learn and see on-site green practices at the university which has already obtained a green card, i.e. has embraced green practices | Freising, DE | 5 | 12 (3 UBN, 3 SVEHERC, 3 CEPS, 3 AUB)

## Slide 22
Task No | Task Name | Description
T2.7 | Provision of recycling points with instructions around buildings and campuses and training of technical staff on recycling points management | In accordance with newly acquired and adopted green practices, and with the aim of making the first steps towards climate neutral universities, a collection of large recycling bins intended for sorting and recycling waste will be deployed around the campuses of target partners´ universities. It is planned to provide 4 recycling points per building. They will come with instructions on how to be used. Technical staff will be trained on how to manage the provided recycling points.
Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB

## Slide 23
Task No | Task Name | Description
T2.8 | Creation and equipping of campus gardens - open air classrooms | Open air classrooms are healthy engaging environments with the assistance of flexible wall openings. Such spaces are stimulating environments without congested atmosphere and stuffy air and without solid wall barriers. Such spaces are environmentally friendly because the ventilation is natural, no electricity is spent on heating and cooling, etc. In order to create such open air classrooms it will be necessary to follow several steps: a) select the proper space; b) request the campus approval; c) the space will be officially registered and it will be assigned a registry number; d) a team will be gathered to create the facility made of staff and students; e) action plan will be made regarding the structure and composition (equipping) of the open classroom (biodiversity, plants, water areas, shelters; f) sustainable green practices will be defined to maintain the site. This activity will be performed in from M24 to M36.
Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB

## Slide 24
Task No | Task Name | Description
T2.9 | Introduction of renewable energy efforts at campuses and LED lights use | Activities intended for introducing renewable energy and LED lights at campuses will include the following: green campaigns and promotion of environmentally friendly campus by suggesting actions such as bike-friendly campus initiatives, creating office materials with recycled paper, replacing light bulbs with LED lights, installing solar chargers for mobile phones, etc. This action will take place in M6-M36
Work Package 2: Optimization of HEIs environment Lead Beneficiary: HSWT, co-lead: AUB

## Slide 25
Deliverables
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS2 | Competent bodies at 4 HEIs adopted ’Towards green university strategies’’ | WP2 | HSWT | Towards green university strategy will be adopted by University Senates of four target Western Balkans universities. The strategy comprises the plan of action of creating, nurturing and maintaining green universities. | M27 | Official decision of 4 University Senates.
D2.1 | Management, teaching, admin. & technical staff improved knowledge on climate-neutral universities
D2.2 | Equipment purchased and installed
D2.3 | Towards green university strategy prepared for adoption at 4 WB partner HEIs
D2.4 | E-manual
D2.5 | Teacher staff trained on ToT skills in 3 fields
D2.6 | Study visit and learning about recycling practices and renewable energy efforts carried out
D2.7 | 4 WB partner HEI buildings equipped with recycling points with instructions
D2.8 | Open air classrooms created
D2.9 | 4 WB partner HEIs improved energy use systems on the campuses
WPs/ t | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X

## Slide 26: Work Package 3: Green transition in teaching, learning & research Lead Beneficiary: AVMSS, co-lead: SVEHERC
Activities
Deliverables
T3.1 | Introduction seminar for teaching staff on green teaching and learning classrooms and methodologies
T3.2 | Creation of video tutorial for teachers on the creation of environmentally friendly teaching forms
T3.3 | Study visit
T 3.4 | Development of green university innovation hackathons
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS3 | Green university innovation hackathons prepared for implementation | WP3 | SUA AVMSS | Preparing implementation of an event such as hackathon implies a detailed action plan foreseeing every step in a successful realization, from the initial idea to the final product and finalized event. | M21 | Hackathons organisation guidelines, comprising an action plan.
D3.1 | 2.1) Management, teaching, adm2.8) in. & technical staff improved knowledge on climate-neutral universities.
D3.2 | Video tutorial
D3.3 | Study visit and learning about student hackathons carried out
D3.4 | Green university innovation hackathons prepared for implementation

## Slide 27: Work Package 3: Green transition in teaching, learning & research Lead Beneficiary: AVMSS, co-lead: SVEHERC
Task No | Task Name | Description
T3.1 | Introduction seminar for teaching staff on green teaching and learning classrooms and methodologies | In the course of M9 a two-day virtual seminar will be organised for the teaching staff, on the topic of green teaching and learning classrooms and methodologies. The teaching staff will be introduced to the methodologies and practices which are aimed at exerting a powerful influence on students in regard to environmental conservation. These methodologies are applied for the purpose of developing an ethical commitment to environmental conservation in students through valuating environmental sustainability. These methodologies comprise the why and how of raising environmental awareness: how to carefully and systematically develop environmental beliefs and values and translate them into environmentally-friendly behaviour. The stated methodologies are grounded in project-based learning and hands-on student activities. The seminar is planned to last for 2 days (5 hours per day). It is intended for 36 participants in total, and it is expected that at least 30% will be women.
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E3.1 | Seminar facilitated by AVMSS | Seminar intended for teaching staff to learn on green teaching and learning classrooms and methodologies (Activity T3.1) | Seminar (training) | Topic: methodologies applied for the purpose of developing an ethical commitment to environmental conservation in students through valuating environmental sustainability. These methodologies comprise the why and how of raising environmental awareness: how to carefully and systematically develop environmental beliefs and values and translate them into environmentally-friendly behaviour | Virtual platform | 2 | 36 (9 UBN, 9 SVEHERC, 9 CEPS, 9 AUB)

## Slide 28: Work Package 3: Green transition in teaching, learning & research Lead Beneficiary: AVMSS, co-lead: SVEHERC
Task No | Task Name | Description
T3.2 | Creation of video tutorial for teachers on the creation of environmentally friendly teaching forms | After the first day of seminar, the WP3 team led by SUA and AVMSS staff will start creating video tutorial for teachers on the creation of environmentally friendly teaching form. The video tutorials will be audio-visual instructions on key methods and techniques applied to create environmentally friendly teaching forms. All materials will be in English, and the videos will have subtitles in Bosnian and Montenegrin languages. The videos will be available at project website and partner HEIs websites.

## Slide 29: Work Package 3: Green transition in teaching, learning & research Lead Beneficiary: AVMSS, co-lead: SVEHERC
Task No | Task Name | Description
T3.3 | Study visit | This study visit will be organized and hosted by AVMSS from Serbia, and assisted by SUA from Slovakia. Sixteen staff members will learn on-site about green teaching and learning classrooms and methodologies. The host AVMSS is a higher education institution whose strength is development of teaching and learning methodologies based on project approach and integrative learning which are in this case pivotal for embracing green practices. Study visit will take place in M? and it will gather 16 participants (4 per target partner university). It is expected that 30% of participants will be women.
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E3.2 | Workshop facilitated by AVMSS Participants: UBN, SVEHERC, CEPS, AUB | Workshop and study visit intended for teaching staff to learn about green teaching and learning methodologies (Activity T3.3) | Study visit & workshop | Workshop and study visit are organised to enable staff members learn on-site about green teaching and learning classrooms and methodologies based on project approach and integrative learning which are in the core of events such as hackathons that are to be organised later in the project. | Kruševac, RS | 5 | 12 (3 UBN, 3 SVEHERC, 3 CEPS, 3 AUB)

## Slide 30: Work Package 3: Green transition in teaching, learning & research Lead Beneficiary: AVMSS, co-lead: SVEHERC
Task No | Task Name | Description
T3.4 | Development of green university innovation hackathons | Hackathons are relatively new events in the Western Balkan countries and four target universities will need to develop guidelines for organizing these complex but innovative events. These guidelines will be developed through one organised online meeting in M21. The meeting is to last for 5 hours and it will include representatives of all partner institutions (at least two per partner, and at least 30% female participants). Participants will decide on the steps as to how to organize hackathons: setting the goal, date, place and time, marketing the event in a green way, recruiting the sponsors, devising registration forms, branding winning ideas, etc.

## Slide 31
Deliverables
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS3 | Green university innovation hackathons prepared for implementation | WP3 | SUA AVMSS | Preparing implementation of an event such as hackathon implies a detailed action plan foreseeing every step in a successful realization, from the initial idea to the final product and finalized event. | M21 | Hackathons organisation guidelines, comprising an action plan.
D3.1 | 2.1) Management, teaching, adm2.8) in. & technical staff improved knowledge on climate-neutral universities.
D3.2 | Video tutorial
D3.3 | Study visit and learning about student hackathons carried out
D3.4 | Green university innovation hackathons prepared for implementation
WPs/ t | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
WP3 |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 32: Work Package 4: Introduction of digital & sustainable academic mobility Lead Beneficiary: SUA, co-lead: CEPS
Activities
Deliverables
T4.1 | Training for administrative and teaching staff on student and staff mobility
T4.2 | Training for student parliaments and organizations on their support role in preparing student for mobility or hosting student mobility
T4.3 | Creation of sending/hosting mobility e-guidelines
T4.4 | Study visit
T4.5 | e-Mentoring of administrative staff regarding hosting/sending students and staff
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS4 | Created sending/hosting mobility e-guidelines | WP4 | SUA | Prepared sending/hosting mobility guidelines comprising necessary steps in a successful realization of digital academic mobility. | M21 | Adopted and published e-guidelines on sending/hosting staff/students mobility
D4.1 | Administrative and teaching staff trained on student and staff mobility
D4.2 | Student parliaments and organizations trained on student mobility
D4.3 | E-guidelines
D4.4 | Administrative and management staff learned about mobility practices
D4.5 | 3 EU partner HEIs provided 6 months e-mentoring support to administrative staff at 4 WB partner HEIs

## Slide 33
Task No | Task Name | Description
T4.1 | Training for administrative and teaching staff on student and staff mobility | In the course of M?, a two-day virtual seminar will be organised for administrative and teaching staff on the topic of digital and sustainable student and staff mobility. The staff will be introduced to the concept of digital mobility: how it is different from traditional academic mobility (advantages and disadvantages), what rules and regulations need to be in place to implement it (credit mobility; evaluation of activities, monitoring mechanisms, etc.); rights and obligations of hosting and sending institutions; rights and obligations of mobility participants, etc. The training is planned to last for 2 days (5 hours per day). It is intended for 24 participants in total, and it is expected that at least 30% will be women.
Work Package 4: Introduction of digital & sustainable academic mobility Lead Beneficiary: SUA, co-lead: CEPS
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E4.1 | Training facilitated by SUA Participants: UBN, SVEHERC, CEPS, AUB | Training delivered with the intention of training the administrative and teaching staff on student and staff mobility (Activity T4.1) | Training | The training will introduce the staff to the concept of digital mobility: how it is different from traditional academic mobility (advantages and disadvantages), what rules and regulations need to be in place to implement it (credit mobility; evaluation of activities, monitoring mechanisms, etc.); rights and obligations of hosting and sending institutions; rights and obligations of mobility participants, etc. | Virtual platform | 2 | 24 (6 UBN, 6 SVEHERC, 6 CEPS, 6 AUB)

## Slide 34
Task No | Task Name | Description
T4.2 | Training for student parliaments and organizations on their support role in preparing student for mobility or hosting student mobility | In the course of M?, a two-day virtual seminar will be organised for student parliament and organizations on their support role in preparing student for mobility or hosting student mobility. The participants will be introduced to the concept of digital mobility: how it is different from traditional academic mobility (advantages and disadvantages), what rules and regulations need to followed to implement it (credit mobility; evaluation of activities, monitoring mechanisms, etc.); rights and obligations of mobility participants, etc. The training is planned to last for 2 days (5 hours per day). It is intended for 36 participants in total, and it is expected that at least 30% will be women.
Work Package 4: Introduction of digital & sustainable academic mobility Lead Beneficiary: SUA, co-lead: CEPS
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E4.2 | Training facilitated by SUA Participants: UBN, SVEHERC, CEPS, AUB | Training delivered with the intention of training the student parliaments and organisation on student and staff mobility (Activity T4.2) | Training | The training will introduce student parliaments and organisations to the concept of digital mobility: how it is different from traditional academic mobility (advantages and disadvantages), what rules and regulations need to be in place to implement it (credit mobility; evaluation of activities, monitoring mechanisms, etc.); rights and obligations of mobility participants, etc. | Virtual platform | 2 | 36 (9 UBN, 9 SVEHERC, 9 CEPS, 9 AUB)

## Slide 35
Task No | Task Name | Description
T4.3 | Creation of sending/hosting mobility e-guidelines | Upon finishing the foreseen training sessions for administrative and teaching staff, SUA will lead the activity of preparing sending/hosting e-guidelines. These guidelines will be used by the administrative and teaching staff as a useful resource on how to prepare, realize and finalize digital and sustainable student/staff mobility. The e-guidelines will cover minimum the following sections: the notion of digital academic mobility and the need for such mobility form; rules and regulations to be followed in order to send/host staff and students; rules and regulations to be followed during the mobility period; rights and obligations of hosting and sending institutions; rights and obligations of mobility participants, etc. The guidelines will be published in English, as well as in Bosnian and Montenegrin.
Work Package 4: Introduction of digital & sustainable academic mobility Lead Beneficiary: SUA, co-lead: CEPS

## Slide 36
Task No | Task Name | Description
T4.4 | Study visit | This study visit will be organized and hosted by SUA and it will take place in Slovakia. Sixteen staff members will learn on-site about preparing staff/student for mobility or hosting staff/student mobility. The host SUA is a higher education institution quite versed in all forms of student/staff mobility and an established green university with a large number of academic activities successfully transferred to the virtual realm. Study visit will take place in M? and it will gather 16 participants (4 per target partner university). It is expected that 30% of participants will be women.
Work Package 4: Introduction of digital & sustainable academic mobility Lead Beneficiary: SUA, co-lead: CEPS
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E4.3 | Workshop facilitated by SUA Participants: UBN, SVEHERC, CEPS, AUB | Workshop delivered with the aim of enabling administrative and management staff to learn about mobility practices (Activity 4.4) | Study visit and workshop | Workshop and study visit will be organised to enable the HEIs non-staff to learn on-site about preparing staff/student for mobility or hosting staff/student mobility. The host SUA is a higher education institution quite versed in all forms of student/staff mobility and an established green university with a large number of academic activities successfully transferred to the virtual realm. | Nitra, SK | 5 | 16 (4 UBN, 4 SVEHERC, 4 CEPS, 4 AUB)

## Slide 37
Task No | Task Name | Description
T4.5 | e-Mentoring of administrative staff regarding hosting/sending students and staff | E-mentoring for administrative staff will be conducted in M? and it will gather 16 participants (4 per target HEI). This form of guided mentoring will take place online by resorting to online software/platforms. This form of mentoring is another example of green practice and it serves to assist the administrative staff in their professional growth through professional dialogue and exchange of opinions and experiences in relation to academic mobility and/or digital academic mobility.
Work Package 4: Introduction of digital & sustainable academic mobility Lead Beneficiary: SUA, co-lead: CEPS

## Slide 38
Deliverables
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS4 | Created sending/hosting mobility e-guidelines | WP4 | SUA | Prepared sending/hosting mobility guidelines comprising necessary steps in a successful realization of digital academic mobility. | M21 | Adopted and published e-guidelines on sending/hosting staff/students mobility
D4.1 | Administrative and teaching staff trained on student and staff mobility
D4.2 | Student parliaments and organizations trained on student mobility
D4.3 | E-guidelines
D4.4 | Administrative and management staff learned about mobility practices
D4.5 | 3 EU partner HEIs provided 6 months e-mentoring support to administrative staff at 4 WB partner HEIs
WPs/ t | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
WP3 |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  | 

## Slide 39: Work Package 5: Communication & exploitation Lead Beneficiary: CEPS, co-lead: SECCG
Activities
Deliverables
T5.1 | Maintenance and promotion of Towards green university website
T5.2 | Creation of policy brief Towards green university
T5.3 | Adoption of ‘’Towards green university’’ strategy
T5.4 | Promotion of policy brief ‘’Towards green university’’ across HE and the society
T5.5 | Publication of annual e-newsletter ‘’Towards green university’’
T5.6 | Local institutional training sessions on recycling culture, green energy sources, infrastructure
T5.7 | Organization of green university innovation hackathons competitions
T5.8 | Final promotional conferences ‘’Towards green university’’
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS5 | Adopted Towards green university strategy | WP5 | HSWT SVEHERC | Towards green university strategy is an all-encompassing document that summarizes the key steps towards the project´s overall aim which is creating green universities and embracing the concept of green transition. | M27 | Official decisions of Senates of four target universities on adopting the Towards green university strategy
MS6 | Creation of Towards green university policy brief across HE and the society | WP5 | HSWT SVEHERC | Policy brief is one step further towards green transition in the Western Balkans region as it offers valuable recommendations and pathways which could lead to further expansion and promotion of green ideas and practices across the region. | M24 | Published policy brief document.
D5.1 | Website recognized by the specific and general communities
D5.2 | Stakeholders made aware of green university policyTowards green university
D5.3 | E-newsletter Towards green university
D5.4 | WB Partner institution teaching and administrative & technical staff trained on recycling culture, green energy sources, infrastructure
D5.5 | 4 institutional hackathon reports
D5.6 | 2 national conference reports

## Slide 40: Work Package 5: Communication & exploitation Lead Beneficiary: HSWT, co-lead: SECCG
Task No | Task Name | Description
T5.1 | Maintenance and promotion of Towards green university website | Project website will be regularly updated with project-related information (communication and dissemination activities, latest achievements, results and milestones, etc.). Information will be uploaded by designated administrators (2 with full access to website parameters) of the project Dissemination team. Project website will contain suitable Erasmus + Programme logo, as well as other required funding and ownership symbols. Links will be created towards individual partner´ websites and the content will be presented in English and/or local partner languages (Bosnian and Montenegrin). Data will be uploaded whenever opportunity presents itself, on average 3 per month.

## Slide 41: Work Package 5: Communication & exploitation Lead Beneficiary: HSWT, co-lead: SECCG
Task No | Task Name | Description
T5.2 | Creation of policy brief Towards green university | A policy brief Towards green university is to be led by P2 and P6 and developed jointly by the partnership. The policy brief will comprise the summary of the main project topic, which is the creation of green universities as well as recommendations, best options and justified reasons on a path towards greening one´s universities. The policy brief is intended for all those who are interested in creating a policy framework for prospective green universities, green communities and green transition in general. Target groups are as follows: autonomous higher education bodies, ministries, government advisors, civil servants, etc. Policy brief aims to secure the sustainability of the project idea by recommending it to a wider community. The policy brief will be available in three languages (English, Bosnian, Montenegrin). It is planned to distribute the policy brief among minimum 200 recipients.

## Slide 42: Work Package 5: Communication & exploitation Lead Beneficiary: HSWT, co-lead: SECCG
Task No | Task Name | Description
T5.3 | Adoption of ‘’Towards green university’’ strategy | During M? of project implementation four strategy documents devised by four target HEIs in collaboration with the partnership will be adopted by four University Senates of target HEIs. Strategies will consequently be incorporated in four statutes of target HEIs thus making the strategy the official policy of the afore-mentioned universities at hand.

## Slide 43: Work Package 5: Communication & exploitation Lead Beneficiary: HSWT, co-lead: SECCG
Task No | Task Name | Description
T5.4 | Promotion of policy brief ‘’Towards green university’’ across HE and the society | The policy brief Towards green university will be promoted though various communication and dissemination activities: project website, individual HEIs websites and social network profiles, all available local and national media in the four target countries, and across Western Balkans, during the final promotional conference, in the newsletter, etc.

## Slide 44: Work Package 5: Communication & exploitation Lead Beneficiary: HSWT, co-lead: SECCG
Task No | Task Name | Description
T5.5 | Publication of annual e-newsletter ‘’Towards green university’’ | Three annual newsletters will be published in the course of the project, and they will continue to be published even after the project lifetime. The newsletter will contain relevant and principal information relating to the project and its achievements. The e-newsletter will be 4-8 pages long and it will contain inputs and contributions from all partner institutions. The e-newsletter will be available in English, Bosnian and Montenegrin. It will be published on the project website and individual websites of all partner institutions.

## Slide 45: Work Package 5: Communication & exploitation Lead Beneficiary: HSWT, co-lead: SECCG
Task No | Task Name | Description
T5.6 | Local institutional training sessions on recycling culture, green energy sources, infrastructure | Training sessions are intended for all stakeholders (teaching, administrative, technical and management staff, student organizations members) at four target HEIs who have the opportunity to further share the knowledge and skills, organize campaigns and animate wider community to participate in the green transition conceived by the GROWTH. Twelve training session in total have been planned at four target universities and they will include 12 participants each. It is expected that 30% will be female participants.
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E5.1 | Training facilitated by UBN, SVEHERC, CEPS, AUB Participants: Teaching and non-teaching staff of UBN, SVEHERC, CEPS, AUB | Training for teaching and non-teaching staff at four HEIs on recycling culture, green energy sources, infrastructure (Activity 5.6) | Training | Training sessions are intended for all stakeholders (teaching, administrative, technical and management staff, student organizations members) at four target HEIs who will thus gain the opportunity to further share the knowledge and skills, organize campaigns and animate wider community to participate in the green transition conceived by the GROWTH. | Virtual platform | 3 | Total: 144 (36 UBN, 36 SVEHERC, 36 CEPS, 36 AUB)

## Slide 46: Work Package 5: Communication & exploitation Lead Beneficiary: HSWT, co-lead: SECCG
Task No | Task Name | Description
T5.7 | Organization of green university innovation hackathons competitions | Four green innovation hackathons have been planned, one at each target HEI. It is expected that there will be 60 participants in total. They will gather around previously jointly devised green goals and ideas with the aim of creating a solution/product the character of which will be environmentally friendly, which will testify to the green university orientation and which will be usable in the refurnished green university habitat. Hackathons have the character of competitions, whereby the best idea will be rewarded and promoted within the project dissemination campaign and beyond.
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E5.2 | Competition and dissemination event delivered by UBN, SVEHERC, CEPS, AUB Participants: students, teaching staff, researchers, non-teaching staff, local community | Competition for HEI stakeholders (Activity 5.7) | Competition and dissemination | Competition is organised with the aim of creating a solution/product the character of which will be environmentally friendly, which will testify to the green university orientation and which will be usable in the refurnished green university habitat. | UBN, SVEHERC, CEPS, AUB | 1 | Total: 60 (20 UBN, 20 SVEHERC, 20 CEPS, 20 AUB)

## Slide 47: Work Package 5: Communication & exploitation Lead Beneficiary: HSWT, co-lead: SECCG
Task No | Task Name | Description
T5.8 | Final promotional conferences ‘’Towards green university’’ | Towards the end of the project, during M36, partner HEIs will host the national dissemination conferences that will have a hybrid form. Two such conferences are planned by the GROWTH proposal and they are planned to gather minimum 120 participants (60 in the physical environment, and at least 60 more in the virtual environment). The conferences are a kind of multiplier events which will serve to showcase and promote project results relating to newly established green practices at four target universities in Western Balkans. By displaying project achievements, conferences will contribute to further raising awareness of climate change, share examples of good practice, pinpoint the barriers and limitations and provide recommendations for future actions. Presenters will be selected from various fields, social and cultural groups: teaching and non-teaching staff, students, university heads and managers, representatives of local self-government and other policy makers, representatives of different groups with fewer opportunities (female participants, persons with physical disabilities, persons from remote/inaccessible regions). They will be invited through and open call, and participation of the afore-mentioned persons with fewer opportunities among speakers and presenters will be favoured.
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E5.3 | Conference hosted by UBN, SVEHERC, CEPS, AUB Participants: students, HE management, teaching staff, researchers, policy makers, non-teaching staff, local community | 2 national dissemination conferences (Activity 5.8) | Conference | The conferences are organised as multiplier events to showcase and promote project results relating to newly established green practices at four target universities in Western Balkans and contribute to further raising awareness of climate change, share examples of good practice, pinpoint the barriers and limitations and provide recommendations for future actions. | UBN, SVEHERC, CEPS, AUB | 1 | Total:150

## Slide 48
Deliverables
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS5 | Adopted Towards green university strategy | WP5 | HSWT SVEHERC | Towards green university strategy is an all-encompassing document that summarizes the key steps towards the project´s overall aim which is creating green universities and embracing the concept of green transition. | M27 | Official decisions of Senates of four target universities on adopting the Towards green university strategy
MS6 | Creation of Towards green university policy brief across HE and the society | WP5 | HSWT SVEHERC | Policy brief is one step further towards green transition in the Western Balkans region as it offers valuable recommendations and pathways which could lead to further expansion and promotion of green ideas and practices across the region. | M24 | Published policy brief document.
D5.1 | Website recognized by the specific and general communities
D5.2 | Stakeholders made aware of green university policyTowards green university
D5.3 | E-newsletter Towards green university
D5.4 | WB Partner institution teaching and administrative & technical staff trained on recycling culture, green energy sources, infrastructure
D5.5 | 4 institutional hackathon reports
D5.6 | 2 national conference reports
WPs/ t | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
WP3 |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  | 
WP5 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X

## Slide 49: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Activities
Deliverables
T6.1 | Implementation of coordination meetings
T6.2 | Implementation of M&E team meetings
T6.3 | Internal verification of results and costs
T6.4 | Mid-term internal project evaluation
T6.5 | Independent project evaluation
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS7 | Produced mid-term internal evaluation report | WP6 | UBN HSWT | This document will be produced after the first 18 months of project implementation. It will encompass full financial report, as well as detailed report on implemented project activities, possible challenges and/or delays. The report will inform the consortium of the current status of the project and provide them with insight into the project flow. | M18 | Mid-term report
D6.1 | Ensured regular project coordination
D6.2 | Ensured regular project quality control
D6.3 | Results and costs internally verified
D6.4 | Independent evaluation report

## Slide 50: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.1 | Implementation of coordination meetings | Coordination meetings will be virtual by nature and they will take place at a regular, previously established pace with the aim of coordinating and harmonizing project activities, tackling challenges and risks, communicating and exchanging updated information, making joint decisions and agreeing on the next steps. The project plans for 24 coordination meetings during the project lifetime with 70% of the consortium attending every meeting. Coordination reports will be produced bi-annually by the project coordinator. They will be available in English.

## Slide 51: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.2 | Implementation of M&E team meetings | Team meetings for the purpose of monitoring and evaluation will be virtual by nature and they will follow up coordination meetings. The Quality Assurance team will have 24 meetings in the course of project lifetime and the project implementation segments scrutinized by these meetings will be as follows: the quality of activities, results, events, management.

## Slide 52: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.3 | Internal verification of results and costs | One of very important project management segments is the internal verification which will be performed twice a year (every six months). The verification will be dealing with the budget expenditure and project results. Consortium members will be obliged to keep regular records and submit regular reports on the spent budget and activities performed. Every subsequent financial instalment will be conditioned by the timely submission of all necessary project reports. To that purpose the partnership will designate a special virtual drive to make the process swift and timely. The internal verification will be in charge of the coordinating institution assisted by HSWT. Upon finishing the report, all partners will be informed about the project advancement and further steps. The report will be available in English and local partner languages.

## Slide 53: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.4 | Mid-term internal project evaluation | Mid-term internal project evaluation will take place halfway through the project implementation. This evaluation will encompass the first 18 months of the project and it is produced with the aim of a timely review of project progress in order to make necessary corrective actions. The mid-term internal evaluation will be done by the coordinating institution on the basis of fully submitted project documentation (financial and of other nature) by each project partner to the virtual drive. The mid-term evaluation report will be produced in English and it will be published on the project website.

## Slide 54: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.5 | Independent project evaluation | External financial verification will be carried out by qualified independent auditor on a yearly basis.

## Slide 55: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Deliverables
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS7 | Produced mid-term internal evaluation report | WP6 | UBN HSWT | This document will be produced after the first 18 months of project implementation. It will encompass full financial report, as well as detailed report on implemented project activities, possible challenges and/or delays. The report will inform the consortium of the current status of the project and provide them with insight into the project flow. | M18 | Mid-term report
D6.1 | Ensured regular project coordination
D6.2 | Ensured regular project quality control
D6.3 | Results and costs internally verified
D6.4 | Independent evaluation report

## Slide 56
WPs/ t | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
WP3 |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  | 
WP5 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
WP6 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
GROWTH 101083212 Workplan