## Slide 1: WP1 PROJECT PREPARATION
Kick-off meeting
29-30 March 2023.
ERASMUS-EDU-2022-CBHE-STRAND-1
ERASMUS-EDU-2022-CBHE
101083212
ERASMUS-AG-LS

## Slide 2: GROWTH 101083212 Workpackages Overview and Deliverables
GROWTH
WP1 Project preparation
WP2 Optimization of HEIs environment
WP3 Green transition in teaching, learning and research
WP5 Communication & exploitation
WP4 Introduction of digital & sustainable academic mobility
WP6 Project management and quality control
D1.1.1 | Project teams created
D1.1.2 | Implementation tools adopted
D1.2 | Teaching and administrative/technical staff improved project implementation, financial management and quality control skills
D1.3 | Website ’Towards green university’’ created for public use
D1.4. | Needs analysis update report
D1.5 | 2 national conferences
D2.1 | Management, teaching, admin. & technical staff improved knowledge on climate-neutral universities
D2.2 | Equipment purchased and installed
D2.3 | Towards green university strategy prepared for adoption at 4 WB partner HEIs
D2.4 | E-manual
D2.5 | Teacher staff trained on ToT skills in 3 fields
D2.6 | Study visit and learning about recycling practices and renewable energy efforts carried out
D2.7 | 4 WB partner HEI buildings equipped with recycling points with instructions
D2.8 | Open air classrooms created
D2.9 | 4 WB partner HEIs improved energy use systems on the campuses
D3.1 | 2.1) Management, teaching, adm2.8) in. & technical staff improved knowledge on climate-neutral universities.
D3.2 | Video tutorial
D3.3 | Study visit and learning about student hackathons carried out
D3.4 | Green university innovation hackathons prepared for implementation
D4.1 | Administrative and teaching staff trained on student and staff mobility
D4.2 | Student parliaments and organizations trained on student mobility
D4.3 | E-guidelines
D4.4 | Administrative and management staff learned about mobility practices
D4.5 | 3 EU partner HEIs provided 6 months e-mentoring support to administrative staff at 4 WB partner HEIs
D5.1 | Website recognized by the specific and general communities
D5.2 | Stakeholders made aware of green university policyTowards green university
D5.3 | E-newsletter Towards green university
D5.4 | WB Partner institution teaching and administrative & technical staff trained on recycling culture, green energy sources, infrastructure
D5.5 | 4 institutional hackathon reports
D5.6 | 2 national conference reports
D6.1 | Ensured regular project coordination
D6.2 | Ensured regular project quality control
D6.3 | Results and costs internally verified
D6.4 | Independent evaluation report

## Slide 3: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
T1.1 | Kick off meeting, creation of project teams and adoption of implementation documents
T1.2 | Initial staff training sessions on project implementation, financial management and quality
T1.3 | Signing of partnership agreements
T1.4 | Creation of ‘’Towards green university’’ website
T1.5 | Update needs analysis of partner WB HEIs to strengthen university green agenda
T1.6 | Introduction conferences in BA and ME
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS1 | Partnership agreements concluded between the coordinator and partner institutions | WP1 | UBN | Partnership agreements signed between the project coordinator and each partner. They will regulate the rights and obligations within the partnership, and distribution of tasks and responsibilities relating to project implementation and achievement of project results. | M1 | Signed partnership agreements
D1.1.1 | Project teams created
D1.1.2 | Implementation tools adopted
D1.1.3 | Partnership agreement – model as for 2020
D1.2 | Teaching and administrative/technical staff improved project implementation, financial management and quality control skills
D1.3 | Website ’Towards green university’’ created for public use
D1.4. | Needs analysis update report
D1.5 | 2 national conferences
Activities
Deliverables

## Slide 4: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.1 | Kick off meeting, creation of project teams and adoption of implementation documents | The kick-off meeting will be organized in a virtual environment and it will host representatives of all partner institutions. It will be organised by the leading partner UBN in the course of the first month of the project (M1). Activities are planned to last for 2 working days and they will be realised in the following manner: 1) the partnership will be acquainted with their respective contractual obligations, the rules of the Action (Erasmus + CBHE), and key aspects of the financial management and administration procedures; 2) the partnership will be introduced in detail to the project structure, devised activities and interventions, results to be achieved; partnership agreement and project implementation tools will be discussed and agreed upon; 3) planned project teams will be established and the partnership will agree on pace, type and frequency of communication. The meeting outcomes will be as follows: agreement on further steps and each partner´s tasks and obligations; structuring project teams (Steering Committee, Quality team, Communication team, + lead/co-lead WP teams); approved set of project implementation documents (Communication, Dissemination and Exploitation Plan, Gantt chart, and Rules of Procedure).
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E1.1 | Participants: UBN, SVEHERC, CEPS, AUB, AVMSS, HSWT, SUA, SECCG | Kick-off meeting (Activity T.1.1) | Meeting] | Areas: Project description, results, activities, indicators, task division, budget, timeline, grant agreement, partnership agreement, project teams, implementation tools, ] | Virtual platform | 2 | 24 (3 UBN, 3 SVEHERC, 3 CEPS, 3 AUB, 3 AVMSS, 3 HSWT, 3 SUA, 3 SECCG)

## Slide 5: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.2 | Initial staff training sessions on project implementation, financial management and quality | The second virtual meeting will be held in the course of the second month (M2) and it will be hosted by P6 (HSWT). The meeting is planned to last for 2 working days and it is intended for project coordinators, members of each project team previously defined during the kick-off meeting, and administrative and financial team members. In the course of this meeting the participants will be trained on project implementation activities: work package coordination, task implementation, monitoring and evaluation of project activities, manners in which project materials and document will be kept and stored and how partners will have access to them, and about the form and frequency of reporting. As to financial management, participants will be trained on how to run financial documentation and keep the financial records: the programme rules regarding different categories of costs (staff costs, travel and subsistence costs, equipment and subcontracting costs, indirect costs, co-financing requirements), time sheets, internal verification procedures, etc. The third segment of these virtual meetings is dedicated to quality assurance and control. Through this training, the relevant staff will be introduced to QA approach and QA plans and instruments previously drafted by the QA team and finalized by participants during the training session. Minimum 48 staff members will be trained in the course of three planned training sessions (16 per session, whereby 30% are expected to be female participants)
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E1.2 | Training delivered by HSWT Participants: UBN, SVEHERC, CEPS, AUB, AVMSS, HSWT, SUA, SECCG, | Staff training on project implementation, financial management and quality control (Activity T1.2) | Training | Topics: project implementation, financial management and quality control | Virtual platform | 3 | 48 (12 UBN, 12 SVEHERC, 12 CEPS, 12 AUB)

## Slide 6: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.3 | Signing of partnership agreements | Once all partners have agreed on the mutual form of the partner agreement, on individual tasks, roles and obligations, as well as on consequences in case of violation of rights and obligations, partnership agreements will be signed and stored according to partners´ initial agreement.
Task No | Task Name | Description
T1.4 | Creation of ‘’Towards green university’’ website | This activity will be initiated in the third month (M3) of the project and it will be a joint activity of all project partners, led by P3 and P5. All participants will be engaged in providing ideas and solution regarding the website visual and structural design, while partners P3 and P5 will take care of the actual creation process.

## Slide 7: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.5 | Update needs analysis of partner WB HEIs to strengthen university green agenda | Upon concluding initial preparatory activities, the project team led by UBN will prepare and conduct an updated needs analysis with the aim of strengthening university green agenda. The updated needs analysis will serve to build up and amend the existing notions of current needs and confirm the strong base for project interventions. It will clearly indicate and/or reconfirm the most acute points requiring urgent intervention and pinpoint suitable paths for enhancing the four HEIs green transition. The activity will be led by the UBN, but it will be a result of a joint effort of all four partner HEIs from Western Balkans (B&H and Montenegro). As to methodology, the needs analysis will be informed by the most recent developments at partner HEIs reflected in the latest activities, evaluation reports and strategies adopted in partner´s institutions. The report on updated needs analysis will be the result of joint effort, but it will be developed and written in English by the UBN. This is the key activity which will enable the project´s transition to WP2.

## Slide 8: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
Task No | Task Name | Description
T1.6 | Introduction conferences in BA and ME | Two conferences are planned within this work package and they will be held in the hybrid environment. Purpose of these conferences will be to present the main findings of the updated needs analysis from four HEIs as well as to present the participants and wider audience with the main project topic (green transition through green practices and environmental awareness resulting in environmentally friendly behaviours and actions) and possible interventions.
Event No (continuous numbering linked to WP) | Participant | Description |  |  |  |  | Attendees
 |  | Name | Type | Area | Location | Duration (days) | Total
E1.3 | Conference hosted by: UBN, SVEHERC, CEPS, AUB Participants: students, teaching staff, non-teaching staff, management, researchers, local community | Introduction conferences in BA and ME (Activity T1.6) | Conference | Four HEIs from B&H and Montenegro will host two introductory conferences to introduce target groups and all potential stakeholders to projects ambitions and aspirations with regards to the topic of environmental awareness climate neutrality and green transition. | UBN, SVEHERC, CEPS, AUB | 1 | Total: 150

## Slide 9: Work Package 1: Project preparation Lead Beneficiary: UBN, co-lead: SUA
D1.1.1 | Project teams created
D1.1.2 | Implementation tools adopted
D1.1.3 | Partnership agreement – model as for 2020
D1.2 | Teaching and administrative/technical staff improved project implementation, financial management and quality control skills
D1.3 | Website ’Towards green university’’ created for public use
D1.4. | Needs analysis update report
D1.5 | 2 national conferences
Deliverables
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS1 | Partnership agreements concluded between the coordinator and partner institutions | WP1 | UBN | Partnership agreements signed between the project coordinator and each partner. They will regulate the rights and obligations within the partnership, and distribution of tasks and responsibilities relating to project implementation and achievement of project results. | M1 | Signed partnership agreements
WPs/ t | Mar | Apr | May | Jun | Jul | Avg | Sep | Oct | Nov | Dec | Jan | Feb
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
WP1 | X | X | X | X | X | X | X | X | X | X | X | X

## Slide 10: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Activities
Deliverables
T6.1 | Implementation of coordination meetings
T6.2 | Implementation of M&E team meetings
T6.3 | Internal verification of results and costs
T6.4 | Mid-term internal project evaluation
T6.5 | Independent project evaluation
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS7 | Produced mid-term internal evaluation report | WP6 | UBN HSWT | This document will be produced after the first 18 months of project implementation. It will encompass full financial report, as well as detailed report on implemented project activities, possible challenges and/or delays. The report will inform the consortium of the current status of the project and provide them with insight into the project flow. | M18 | Mid-term report
D6.1 | Ensured regular project coordination
D6.2 | Ensured regular project quality control
D6.3 | Results and costs internally verified
D6.4 | Independent evaluation report

## Slide 11: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.1 | Implementation of coordination meetings | Coordination meetings will be virtual by nature and they will take place at a regular, previously established pace with the aim of coordinating and harmonizing project activities, tackling challenges and risks, communicating and exchanging updated information, making joint decisions and agreeing on the next steps. The project plans for 24 coordination meetings during the project lifetime with 70% of the consortium attending every meeting. Coordination reports will be produced bi-annually by the project coordinator. They will be available in English.

## Slide 12: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.2 | Implementation of M&E team meetings | Team meetings for the purpose of monitoring and evaluation will be virtual by nature and they will follow up coordination meetings. The Quality Assurance team will have 24 meetings in the course of project lifetime and the project implementation segments scrutinized by these meetings will be as follows: the quality of activities, results, events, management.

## Slide 13: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.3 | Internal verification of results and costs | One of very important project management segments is the internal verification which will be performed twice a year (every six months). The verification will be dealing with the budget expenditure and project results. Consortium members will be obliged to keep regular records and submit regular reports on the spent budget and activities performed. Every subsequent financial instalment will be conditioned by the timely submission of all necessary project reports. To that purpose the partnership will designate a special virtual drive to make the process swift and timely. The internal verification will be in charge of the coordinating institution assisted by HSWT. Upon finishing the report, all partners will be informed about the project advancement and further steps. The report will be available in English and local partner languages.

## Slide 14: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.4 | Mid-term internal project evaluation | Mid-term internal project evaluation will take place halfway through the project implementation. This evaluation will encompass the first 18 months of the project and it is produced with the aim of a timely review of project progress in order to make necessary corrective actions. The mid-term internal evaluation will be done by the coordinating institution on the basis of fully submitted project documentation (financial and of other nature) by each project partner to the virtual drive. The mid-term evaluation report will be produced in English and it will be published on the project website.

## Slide 15: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Task No | Task Name | Description
T6.5 | Independent project evaluation | External financial verification will be carried out by qualified independent auditor on a yearly basis.

## Slide 16: Work Package 6: Project management and quality control Lead Beneficiary: UBN, co-lead: HSWT
Deliverables
Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification
MS7 | Produced mid-term internal evaluation report | WP6 | UBN HSWT | This document will be produced after the first 18 months of project implementation. It will encompass full financial report, as well as detailed report on implemented project activities, possible challenges and/or delays. The report will inform the consortium of the current status of the project and provide them with insight into the project flow. | M18 | Mid-term report
D6.1 | Ensured regular project coordination
D6.2 | Ensured regular project quality control
D6.3 | Results and costs internally verified
D6.4 | Independent evaluation report